## Sheet1
Street | Location | Begin | End | Length (ft) | Tier | Survey/Design Cost | Engineering/Construction Cost | Total Cost | Survey/Design Begins (Fiscal Year) | Engineering/Construction Begins (Fiscal Year)
8th Street NE | West | E Market Street | 700 E Jefferson | 290 | Tier 1 | 39529.9954 | 92800 | 132329.9954 | 2024 | 2024
Hazel Street | Southwest | E High Street | 1424 Hazel | 80 | Tier 1 | 10904.8263 | 25600 | 36504.8263 | 2024 | 2024
Prospect Avenue | Southeast | Existing | Existing | 645 | Tier 1 | 87920.1621 | 206400 | 294320.1621 | 2024 | 2024
Sycamore Street | North | St. Charles Avenue | 601 Locust Avenue | 150 | Tier 1 | 21059.9458 | 57600 | 78659.9458 | 2025 | 2025
9th Street SW | East | Elm Street | Existing | 760 | Tier 1 | 106703.7254 | 291840 | 398543.7254 | 2025 | 2025
11th Street NW | West | West Street | Existing | 200 | Tier 1 | 28079.9277 | 76800 | 104879.9277 | 2025 | 2026
10 1/2 Street NW | East | Grady Avenue | West Street | 420 | Tier 1 | 58967.8483 | 161280 | 220247.8483 | 2025 | 2026
Orange Street | West | Poplar Street | Existing | 200 | Tier 1 | 28897.7897 | 76800 | 105697.7897 | 2026 | 2027
Orange Street | East | E High Street | Existing | 80 | Tier 1 | 11559.1159 | 30720 | 42279.1159 | 2026 | 2027
Blenheim Avenue | South | Existing | Rialto Street | 200 | Tier 1 | 29715.6517 | 76800 | 106515.6517 | 2027 | 2027
Montrose Avenue | South | Avon Street | Rialto Street | 350 | Tier 1 | 52002.3905 | 134400 | 186402.3905 | 2027 | 2027
Riverdale Drive | Southwest | 1319 Riverdale Drive | Willow Drive | 120 | Tier 1 | 18320.1082 | 46080 | 64400.1082 | 2028 | 2028
St. Claire Avenue | Northwest | Peartree Ln | Smith Street | 280 | Tier 1 | 42746.9191 | 107520 | 150266.9191 | 2028 | 2028
Blenheim Avenue | North | Rialto Street | Meridian Street | 500 | Tier 1 | 76333.7842 | 192000 | 268333.7842 | 2028 | 2029
Blenheim Avenue | North | Existing | Avon Street | 260 | Tier 1 | 39693.5678 | 99840 | 139533.5678 | 2028 | 2029
Bolling Avenue | Either | Avon Street | 6th Street SE | 470 | Tier 1 | 71753.7571 | 180480 | 252233.7571 | 2028 | 2029
W Main Street | South | Ridge Street | Existing | 150 | Tier 2 | 21059.9458 | TBD | TBD | 2025 | 2025
Little High Street | Both | 12th Street NE | Meade Avenue | 1050 | Tier 2 | 147419.6206 | TBD | TBD | 2025 | 2025
Greenleaf Lane | North | Gentry Lane | Rose Hill Drive | 2800 | Tier 2 | 202284.528 | TBD | TBD | 2026 | 2026
Oakleaf Lane | North | Greenleaf Lane | RoseHIll Drive | 1100 | Tier 2 | 93917.8166 | TBD | TBD | 2026 | 2026
9th Street NW | Both | Preston Avenue | West Street | 450 | Tier 2 | 65020.0269 | TBD | TBD | 2026 | 2026
Albemarle Street | Northwest | Dale Avenue | Rivanna Avenue | 1300 | Tier 2 | 193151.736 | TBD | TBD | 2027 | 2027
Druid Avenue | Southwest | Monticello Avenue | Rialto Street | 1500 | Tier 2 | 222867.3877 | TBD | TBD | 2027 | 2027
Poplar Street | North | St. Claire Avenue | Gillespie Avenue | 570 | Tier 2 | 84689.6073 | TBD | TBD | 2027 | 2027
Kelley Avenue | East | Taylor Street | Lexington Avenue | 1000 | Tier 2 | 152667.5683 | TBD | TBD | 2028 | 2028
Franklin Street | Northwest | Carlton Ave | Nassau St | 1300 | Tier 2 | 198467.8388 | TBD | TBD | 2028 | 2028
E Market Street | South | Franklin Street | Meade Avenue | 1400 | Tier 2 | 219459.6294 | TBD | TBD | 2029 | 2029
Blenheim Avenue | North | Castalia Street | Monticello Avenue | 435 | Tier 2 | 68189.242 | TBD | TBD | 2029 | 2029
6th Street SE | West | Montrose Avenue | Blenheim Avenue | 100 | Tier 2 | 15675.6878 | TBD | TBD | 2029 | 2029
Montrose Avenue | Northeast | Avon Street | 6th Street SE | 470 | Tier 2 | 73675.7327 | TBD | TBD | 2029 | 2029
Cedar Hill Road | Either | Hydraulic Road | N Berkshire Road | 1070 | Tier 2 | 167729.8596 | TBD | TBD | 2029 | 2029
Elliot Avenue | North | Ridge Street | Avon Street | 1320 | Tier 2 | 212316.9682 | TBD | TBD | 2030 | 2030
18th Street NE | Both | Little 18th Street | E Market Street | 735 | Tier 2 | 118221.9482 | TBD | TBD | 2030 | 2030
Fairway Avenue | Either | Chesapeake Street | 317 Fairway | 400 | Tier 2 | 64338.4752 | TBD | TBD | 2030 | 2030
Barracks Road | Southwest | Existing | 250 Bypass | 530 | Tier 2 | 85248.4797 | TBD | TBD | 2030 | 2030
Jefferson Park Avenue | North | McCormick | W Main Street | 3700 | Tier 3 | TBD | TBD | TBD | TBD | TBD
Rugby Road Extended | West | Dairy Road | 250 Ramp | 2600 | Tier 3 | TBD | TBD | TBD | TBD | TBD
Locust Avenue | Northwest | Poplar Street | Calhoun Street | 2920 | Tier 3 | TBD | TBD | TBD | TBD | TBD
Alta Vista Avenue | Southwest | Monticello Avenue | 6th Street SE | 2600 | Tier 3 | TBD | TBD | TBD | TBD | TBD
Emmet Street N | West | Stadium Road | McCormick | 485 | Tier 3 | TBD | TBD | TBD | TBD | TBD
Yorktown Drive | Northwest | Grove Road | Bunkerhill Drive | 2700 | Tier 3 | TBD | TBD | TBD | TBD | TBD
St. Clair Avenue | Northwest | Calhoun Street | Hazel Street | 2270 | Tier 3 | TBD | TBD | TBD | TBD | TBD
Rugby Road | North | Rugby Place | Preston Avenue | 1400 | Tier 3 | TBD | TBD | TBD | TBD | TBD
Montrose Avenue | North | Monticello Avenue | Avon Street | 2000 | Tier 3 | TBD | TBD | TBD | TBD | TBD
E High Street | Both | Locust Ave | Long St | 3750 | Tier 3 | TBD | TBD | TBD | TBD | TBD
Jefferson Park Avenue | Southwest | Park Road | Camellia Drive | 1800 | Tier 3 | TBD | TBD | TBD | TBD | TBD
McIntire Road | West | Schenk's Greenway | County Office Building | 1000 | Tier 3 | TBD | TBD | TBD | TBD | TBD